## Sheet1
	User Story	Tasks	Not Started	In Progress	For Review	Complete
U-1	As a user, I want to communicate the waypoints to the UAV.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous method/interface for communicating coordinates to UAV.				10/05/15
		Review code that communicates with quadrotor				10/16/15
		Review code that allows a user to input waypoints				10/16/15
		Modify/Rewrite imlementation as necessary		11/27/15
O-1	As an owner, I want the UAV to autonomously take-off from the landing pad.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for autonomous take-off.				10/05/15
		Review code that enables the quadrotor to autonomously take-off from landing pad				10/16/15
		Modify/Rewrite take-off imlementation as necessary		11/27/15
O-2	As an owner, I want the UAV to autonomously navigate through a set of waypoints.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for navigating waypoints.				10/05/15
		Review code that enables the quadrotor to autonomously navigate through a series of way-points				10/16/15
		Modify/Rewrite implementation as necessary		11/27/15
O-3	As an owner, I want the UAV to autonomously return to the location of the landing pad.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation to autonomously return to location of landing pad				10/05/15
		Review code that allows the autonomous return of the UAV to the landing pad.				10/16/15
		Modify/Rewrite implementation as necessary		11/27/15
O-4	As an owner, I want the UAV to autonomously land on the landing pad without damaging the craft	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for autonomous landing				11/02/15
		Install previous implementation				10/19/15
		Test previous implementation				10/26/15
		Modify/Rewrite implementation as necessary		10/30/15
O-5	As an owner, I want the UAV to autonomously land on the landing pad with the correct orientation.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for autonomous landing				11/02/15
		Install previous implementation				10/19/15
		Test previous implementation				10/26/15
		Modify/Rewrite implementation as necessary		10/30/15
	Initial Common Tasks	Install Ubuntu 14.04 or some other ROS Indigo/Jade distro compliant OS.				09/25/15
		Setup Gazebo 6.+				09/25/15
		Download Rviz package				09/25/15
		Setup Simulation Environment				11/02/15
		Review previous iteration of project documentation				09/25/15
		Inspect current quadrotor configuration				09/28/15
		Identify parts needed for quadrotor				11/02/15
		Acquire parts needed for quadrotor				12/01/15
		Build UAV		11/20/15
		Test flight under manual control	X