## Sheet1
	User Story	Tasks	Not Started	In Progress	For Review	Complete
U-1	As a user, I want to communicate the waypoints to the UAV.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous method/interface for communicating coordinates to UAV.	X
		Review code that communicates with quadrotor		X
		Review code that allows a user to input waypoints		X
		Install previous implementation	X
		Test previous implementation	X
		Modify/Rewrite imlementation as necessary	X
O-1	As an owner, I want the UAV to autonomously take-off from the landing pad.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for autonomous take-off.		X
		Review code that enables the quadrotor to autonomously take-off from landing pad		X
		Install previous implementation of autonomous take-off	X
		Test previous implementation in simulation	X
		Modify/Rewrite take-off imlementation as necessary	X
O-2	As an owner, I want the UAV to autonomously navigate through a set of waypoints.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for navigating waypoints.		X
		Review code that enables the quadrotor to autonomously navigate through a series of way-points		X
		Install previous implementation of autonomous navigation	X
		Test previous implementation	X
		Modify/Rewrite implementation as necessary	X
O-3	As an owner, I want the UAV to autonomously return to the location of the landing pad.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation to autonomously return to location of landing pad	X
		Review code that allows the autonomous return of the UAV to the landing pad.	X
		Install previous implementation	X
		Test previous implementation	X
		Modify/Rewrite implementation as necessary	X
O-4	As an owner, I want the UAV to autonomously land on the landing pad without damaging the craft	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for autonomous landing	X
		Review code that allows the autonomous return of the UAV to the landing pad.	X
		Install previous implementation	X
		Test previous implementation	X
		Modify/Rewrite implementation as necessary	X
O-5	As an owner, I want the UAV to autonomously land on the landing pad with the correct orientation.	INITIAL COMMON TASKS	Status Below	Status Below	Status Below	Status Below
		Review previous implementation for autonomous landing	X
		Review code that allows the autonomous return of the UAV to the landing pad.	X
		Install previous implementation	X
		Test previous implementation	X
		Modify/Rewrite implementation as necessary	X
	Initial Common Tasks	Install Ubuntu 14.04 or some other ROS Indigo/Jade distro compliant OS.				09/25/15
		Setup Gazebo 6.+				09/25/15
		Download Rviz package				09/25/15
		Setup Simulation Environment		X
		Review previous iteration of project documentation				09/25/15
		Inspect current quadrotor configuration				09/28/15
		Identify parts needed for quadrotor				09/28/15
		Acquire parts needed for quadrotor		X
		Add needed parts to quadrotor	X
		Test flight under manual control	X